## Sheet1
| BMP Roadmap | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8
WEEK 1 | Login/Logout | WEEK 1: Login page
Logout page/link
Start Session
End Session
Implement .Net Form Authentication
| Register/Setup Device | WEEK 1: Setup Device page
Save device info in Database
Send Verification Email
Manage several devices page
| Setup Test Environment | WEEK 1: Setup web hosting for Test
Setup database for Test
Setup Cloud locations for Test
Setup Security for Test
WEEK 2 | Forgot Password | WEEK 2: Forgot Password page
Send Reset Password Email
Confirmation for new password page
| Reset Password | WEEK 2: Reset password page
Send Verification Email
Confirmation for new password page
| Change Storage Location | WEEK 2: Change Storage Location page
Offer different cloud locations
Set security for storage locations
| Design/Create All User Interfaces | WEEK 2: Design responsive user interfaces
Write client-side code for all interfaces
WEEK 3 | Report/Query Videos | WEEK 3: Report/Query page (API service for page functions)
Build Data Layer to query database
Add sorting and filtering for result list
| Share Reports/Queries | WEEK 3: Add ability to email report w/video links
Add ability to export to PDF w/video links
Add ability to print reports
Add ability to save reports
| Departments, Workstations, Disk Space, Servers | WEEK 3: Create API service to manage departments
Create API service to manage workstations
Create API service to manage disk space
Create API service to manage servers
WEEK 4 | Upload Videos | WEEK 4: Create web service to upload asynchronously
Create video upload status page
Secure uploaded videos & service to upload
Allow options to upload to different locations
| User Management, User Rights | WEEK 4: API service to manage users
API service to manager permissions
| Account Management | WEEK 4: API service to manage account
Employ .Net Form Auth/Authorization
WEEK 5 | Download Videos | WEEK 5: Add ability to download videos after querying
Add ability to choose where to save videos
| Share Videos | WEEK 5: Add ability to share links via Email & link
Add ability to share sections of video via Email & link
| Download Query | WEEK 5: Add this report to Report API service
| Upload Set | WEEK 5: API service to upload in bulk
WEEK 6 | Important Level | WEEK 6: API Report for Important Level
| Time Period | WEEK 6: API Report for Time Period
| Police Statistics | WEEK 6: API Report for Police Stats
| System Log | WEEK 6: API service to log all actions
| Notice | WEEK 6: API service to set notices
| Preview Settings | WEEK 6: API service to set Preview Settings
| Statistical Dataset | WEEK 6: API service to email statistical data
WEEK 7 | Language Localization/Globalization | WEEK 7: Language Implementation
| Edit Videos | WEEK 7: Add ability to cut sections of video and save them
Add ability to set markers in video
Add ability to delete videos
WEEK 8 | Edit Videos | WEEK 8: Continue API service development for editing videos
| Deployment to Web | WEEK 8: Setup web hosting for Production
Setup database for Production
Setup Cloud locations for Production
Setup Security for Production